Insert Company Logo      ITP - INSPECTION TEST PLAN EXAMPLE,


	Inspection Test Plan Title: 
	Typical Dincel Wall Installation
	Contractor:
	

	Project Name:
	
	Date:
	

	Project Address:
	
	ITP No:
	

	Client:
	
	ITP Work area:
	


	Item No.
	Inspection / Test Point Work Activity
	Timing / Frequency
	Method
	Inspection / Verification / Test Done By
	Acceptance Criteria
	References (Procedure, Specifications, Dwg No, Aust Standards, Consultants Report)
	Comments / Record Type
	NC No


	Sign off as Completed

	
	
	
	
	Client
	Contractor
	Other
	Persons Name
	Signature
	Date
	
	
	
	Non-Conformance Number

	Name 
	Signature
	Date

	1
	Drawings Check
	Per level
	Check latest revisions
	
	R
	
	
	
	
	Ensure all design drawings, specifications and procedures are current
Qualified Structural Engineer design


	Drawing No:

Rev:

Drawing No:

Rev:

Drawing No:

Rev:
	
	
	
	
	

	2
	Site Risk Assessment
	Prior to starting on site 
	Visual
	
	R
	
	
	
	
	Assess all risks relating to the site and document accordingly eg gas location, power lines and the like


	
	
	
	
	
	

	3
	Site Induction
	Prior to starting on site
	Visual
	
	PM
	
	
	
	
	A general construction induction card is required for workers who want to carry out construction work 

All site related personnel to be site inducted prior to commencing works on site


	
	
	
	
	
	

	4
	SWMS
	Prior to starting on site
	Visual
	
	PM
	
	
	
	
	All site related personnel have contributed to, read and signed the relevant SWMS prior to commencing works on site.

 
	
	
	
	
	
	

	5
	Set Out Check
	Prior to Install
	Set out by client
Visual by installer
	
	V
	
	
	
	
	As per current Surveyor set out documents/drawings 


	
	
	
	
	
	

	6
	Install - Walls
	Each work area
	Visual
	
	W
	
	
	
	
	Installed according to builders set out, plumbed and straightened with correct fixings
	AS3610 - Formwork code
	
	
	
	
	

	7
	Install - Corners
	Each work area
	Visual
	
	W
	
	
	
	
	Installed plumb and square to all adjacent walls
	
	
	
	
	
	

	8
	Install – Lintels and Sills
	Each work area
	Visual
	
	W
	
	
	
	
	Installed as per shop drawing dimensions and levels.

	
	
	
	
	
	

	9
	Install - Doors
	Each work area
	Visual
	
	W
	
	
	
	
	Installed plumb, in wind and braced with timbers.

	
	
	
	
	
	

	10
	Install - Reinforcement
	Each work area
	Visual
	
	W
	
	
	
	
	Installed as per Engineers instruction with appropriate lapping.
	
	
	
	
	
	

	11
	Install – epoxy starter bars floor to wall connections *(scope dependant)
	Each work area
	Visual
	
	W
	
	
	
	
	Installed as per Engineers instruction with appropriate lapping.
	
	
	
	
	
	

	12
	Bracing by Wall Installer
	Each work area
	Visual
	
	W
	
	
	
	
	All Dincel elements braced and all fixings are secure


	
	
	
	
	
	

	13
	Bracing by Builder
	Each work area
	Visual
	
	R
	builder
	
	
	
	Any out of scope bracing to walls
	
	
	
	
	
	

	14
	Formwork by builders contractor
	Each work area
	Visual
	
	R
	builder
	
	
	
	Formwork deck installed to correct dimensions and RL’s
	
	
	
	
	
	

	15
	Modifications by Wall Installer
	Each work area
	Visual
	
	R
	
	
	
	
	Set down cuts, and part of scope penetrations done.

	
	
	
	
	
	

	16
	Modifications by Builder
	Each work area
	Visual
	
	R
	builder
	
	
	
	Any AUTHORISED penetrations and RL’s cut and patched to VO’s detail.
	
	
	
	
	
	

	17
	Modifications by trades
	Each work area
	Visual
	
	R
	builder
	
	
	
	Any AUTHORISED penetrations, lift call boxes cut and patched.
	
	
	
	
	
	

	18
	Reinforcement inspection
	Each work area
	Checked
	
	HOLD
	engineer
	
	
	
	All steel reinforcement installed in Dincel walls inspected by builder / engineer.

	
	
	
	
	
	

	19
	Concrete confirmation
	Each work area
	Visual
	
	V
	
	
	
	
	SPECIFIED concrete supply confirmed and notarised.
	
	
	
	
	
	

	20
	Concrete order
	Each work area
	Visual
	
	V
	
	
	
	
	Date of pour confirmed with builder, pump booked and adequate platforms available.

	AS3600 – Concrete strength

AS3972 – Cement type
AS3582.1 – Fly Ash
	Concrete strength required ………. mpa strength ordered

Slump required by engineer …….… slump ordered

Concrete test ordered  yes / no

Dispensing Concrete method Pump / Chute


	
	
	
	

	21
	Pre pour Wall check
	Each work area
	Visual
	
	W
	
	
	
	
	All walls have remained plumb and straight upon inspection.

	
	
	
	
	
	

	22
	Caps to end of wall check
	Each work area
	Visual
	
	W
	
	
	
	
	All caps are appropriately braced or strapped.
	
	
	
	
	
	

	23
	Door and window opening check
	Each work area
	Visual
	
	W
	
	
	
	
	All windows checked for installed propping and doors for installed timber spreaders.
	
	
	
	
	
	

	24
	Concrete delivery checks
	Each truck / delivery
	Visual
	
	HOLD
	
	
	
	
	1: design mix / MPA and slump checked against supplier delivery dockets and notarised.

2: visual inspection checks carried out on initial discharge of concrete.


	
	
	
	
	
	

	25
	Pour Wall
	Each work area
	Visual
	
	W
	
	
	
	
	Pour walls carefully as suggested in the Dincel construction Manual, and monitor caps at ends of walls.

	
	
	
	
	
	

	26
	Pour door lintels
	Each work area
	Visual
	
	W
	
	
	
	
	Pour doors carefully, ensure no voids are present and monitor for door frame failure.
	
	
	
	
	
	

	27
	Pour window lintels
	Each work area
	Visual
	
	W
	
	
	
	
	Pour windows carefully, ensure no voids are present and monitor for lintel failure.
	
	
	
	
	
	

	28
	Compression Test
	Every 50m3
	checked
	
	W
	
	
	
	
	Sample taken in accordance with Australian Standards and or Project Engineers Instructions.
	AS1012 and AS1379 – 2007
( Clause 6.5.2 )
	
	
	
	
	

	29
	Clean Walls
	Each work area
	Visual
	
	W
	
	
	
	
	All wall surfaces/bases cleaned including removing rubbish to bin / designated area.
	
	
	
	
	
	

	30
	Clean door frames
	Each work area
	Visual
	
	W
	
	
	
	
	All frame surface cleaned 
	
	
	
	
	
	

	31
	Clean Window areas
	Each work area
	Visual
	
	W
	
	
	
	
	All window sills trowel finished and all edges of window opening cleaned
	
	
	
	
	
	

	32
	Clean formed deck
	Each work area
	Visual
	
	W
	
	
	
	
	All concrete splatter from wall pour cleaned 
	
	
	
	
	
	

	33
	Trade defects
	Each work area
	Visual
	
	V
	Builder
	
	
	
	ALL TRADE related defects work identified, reported and rectified appropriately.

	
	
	
	
	
	

	34
	Wall Installers defects
	Each work area
	Visual
	
	V
	
	
	
	
	ALL Wall Installer related defects work identified, reported and rectified appropriately.


	
	
	
	
	
	

	35
	Inspection and Hand Over
	Upon Completion
	Final Inspection
	
	V
	Builder
	
	
	
	Inspection and signoff by client/builder for the completion of works by wall installer. All items complete to specifications.


	Client satisfaction
	
	
	
	
	


	Non-Conformances:

	Item No.
	NC No.
	Description
	Corrective Action Required
	Responsible Party
	Date to be Completed
	Verified as Actioned By
	Date Closed Out

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	


	Comments:

	

	

	

	


	Verified by Client: if required
	Verified by Contractor: 
	Verified by Other: if required

	Company Name:
	
	Company Name:
	
	Company Name:
	

	Print Name:
	
	Print Name:
	
	Print Name:
	

	Position/Title:
	
	Position/Title:
	
	Position/Title:
	

	Signature:
	
	Signature:
	
	Signature:
	

	Date:
	
	Date:
	
	Date:
	


	Legend

	W = Witness
	The Contractor, Engineer or Consultant may inspect, test, review, witness the work. The activities however may proceed.

	H = Hold Point
	Performance of an activity must be stopped and put on hold until specified actions are completed and have been passed/approved.

	V = Verify
	A verification document, drawing, photo, specification, report or the like is provided and attached to this ITP.

	NC = Non-Conformance
	A Non-Conformance is raised where a work item, activity or the like does not comply

	S = Surveillance or monitoring
	Monitor the status of work and materials and analyses of records on a periodical basis to ensure that specified requirements are being fulfilled.

	R = Review
	Review, record, document the results of inspection, examination or test to ensure the results have passed

	PM
	Project Manager

	CA
	Contracts Administrator


ITP No:                     Page | 2

